## Slide 1: Project timeline ver 1.0
Notes: A simplified version of timeline

## Slide 2
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
30 Jul – 7 Aug
Brainstorming Session
Project Initiation
Client Interaction
Proposal Planning
25 Aug – 9 Sept
UI Mockup
Use Case
Risk Mitigation Plans
Metrics Structure
Research & Learn
Set Up Environment
11 Sept – 21 Sept
Set Up Database
User Account Module:
  Login/Logout
  Create/Edit Account
  Password Reset
Learn to integrate with Trello
24 Sept – 8 Oct
Project Module:
  Create/View/Edit/Delete using Trello
  Browse Sub-projects List
  View Project Details
  Sort Projects
  Create Dashboard
  Filter Dashboard
  Enhance Dashboard UI
Quotation Module:
  Create/View/Edit Quotation w/o Preset Modules
  Create Payment Plan
12 Oct – 21 Oct
Project Module:
  View Project Timeline
  Cross-filter Projects
  Enhance UI
  Assign Staff
  Display Statistics
Staff Module:
  Create/Edit Staff
Finalize Proposal
23 Oct – 31 Oct
Quotation Module:
  Create/View/Edit Quotation with Preset Modules
Invoice Module:
  Create/View/Edit Invoice
Contract Module:
  Create/View/Edit Invoice
Sign-Off Module:
  Create/View/Edit Invoice
Bug Logbook Module:
  Create/View/Edit Invoice
NDA Module:
  Create/View/Edit Invoice
Prepare Acceptance
6 Nov – 16 Nov
Master Setup Module:
  Create/View/Edit Document Templates
  Create/View/Edit Preset Quotation Modules
Product Module:
  Create/View/Edit
  Product Info
Hardware Resource Module:
  Create/View/Edit Hardware Resource
23 Dec – 1 Jan
Hardware Resource Module:
  Assign Resource to Project
Project Module:
  Integrate Resource to Project
Staff Portfolio Module:
  View Staff Portfolio
  Filter Projects by Status
  View Project
4 Jan – 17 Jan
Project Module:
  Notification Log
User Account Module:
  Deactivate Account
Staff Module:
  Deactivate Staff
Quotation Module:
  Deactivate Quotation
Invoice Module:
  Deactivate Invoice
Contract Module:
  Deactivate Contract
Sign-Off Module:
  Deactivate Sign-off
Bug Logbook Module:
  Deactivate Bug Logbook
NDA Module:
  Deactivate NDA
20 Jan – 6 Feb
Business Intelligence:
  Generate Staff & Project Charts
  Sort Staff Chart
  Sort Project Chart
User Account Module:
  User Access Control
  Time-based Security
Optimization:
  Enhance UI
  Update APIs
10 Feb – 21 Feb (Target Go-Live)
Optimization:
  Dynamic Page Replacing Content
  Update APIs
Project Module:
  News Feed
Prepare for Midterm
28 Feb – 14 Mar
Improve from User Feedback
Project Module:
  Export to CSV
Quotation Module:
  Export to CSV
Invoice Module:
  Export to CSV
17 Mar – 28 Mar
Tidy Up Codes
Optimization:
  Enhance UI
Explore Optional Features
Prepare for Poster
31 Mar – 10 Apr
Project Closure
Prepare for Final Presentation
Prepare for Poster Day
5 Dec – 19 Dec
Staff Module:
  Generate & View Portfolio
Staff Portfolio Module:
  View Staff Portfolio
  Filter Projects by Status
  View Project
Quotation Module:
  Generate in PDF
  Email to Client
Invoice Module:
  Generate in PDF
  Email to Client
Contract Module:
  Generate in PDF
  Email to Client
Sign-Off Module:
  Generate in PDF
  Email to Client
Bug Logbook Module:
  Generate in PDF
NDA Module:
  Generate in PDF
  Email to Client
Proposal
20 Oct
Acceptance
3-5 Nov
Midterm
24 – 27 Feb
Poster
30 Mar
Final Presentation
13 – 21 Apr
Poster Day
22 Apr
Notes: A detailed version of timeline

## Slide 3
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
30 Jul – 7 Aug
Project Initiation
25 Aug – 9 Sept
Designing and Diagramming
11 Sept – 21 Sept
User Account Module
Project Module
24 Sept – 8 Oct
Project Module
Quotation Module
12 Oct – 21 Oct
Project Module
Staff Module
UI Enhancement
Finalize Proposal
23 Oct – 31 Oct
Quotation Module
Invoice Module
Contract Module
Sign-Off Module
Bug Logbook Module
NDA Module
Prepare Acceptance
6 Nov – 16 Nov
Master Setup Module
Product Module
Hardware Resource Module
23 Dec – 1 Jan
Hardware Resource Module
Project Module
Staff Portfolio Module
4 Jan – 17 Jan
Project Module
User Account Module
Staff Module
Quotation Module
Invoice Module
Contract Module
Sign-Off Module
Bug Logbook Module
NDA Module
20 Jan – 6 Feb
Business Intelligence:
User Account Module
Optimization
10 Feb – 21 Feb (Target Go-Live)
Optimization
Project Module
Prepare for Midterm
28 Feb – 14 Mar
Improve from User Feedback
Project Module
Quotation Module
Invoice Module
17 Mar – 28 Mar
Tidy Up Codes
UI Enhancement
Explore Optional Features
Prepare for Poster Day
31 Mar – 10 Apr
Project Closure
Prepare for Final Presentation
Prepare for Poster Day
5 Dec – 19 Dec
Staff Module
Staff Portfolio Module
Quotation Module
Invoice Module
Contract Module
Sign-Off Module
Bug Logbook Module
NDA Module
Proposal
20 Oct
Acceptance
3-5 Nov
Midterm
24 – 27 Nov
Poster
30 Mar
Final Presentation
13 – 21 Apr
Poster Day
22 Apr
Notes: A simplified version of timeline

## Slide 4: Project timeline ver 2.0
Edited the modules to be done in iter 4 and included UAT milestones

## Slide 5
1
Proposal
20 Oct
30 Jul – 7 Aug
Brainstorming Session
Project Initiation
Client Interaction
Proposal Planning
25 Aug – 9 Sept
UI Mockup
Use Case
Risk Mitigation Plans
Metrics Structure
Research & Learn
Set Up Environment
11 Sept – 21 Sept
Set Up Database
User Account Module:
  Login/Logout
  Create/Edit Account
  Password Reset
Learn to integrate with Trello
12 Oct – 21 Oct
Project Module:
  Create/Edit Sub-Projects
  View Sub-Projects in Project Schedule
  Create Dashboard
  Create Simulation on Dashboard
  Create Project from Simulation
Staff Module:
  View Projects in Staff Portfolio
  View Tasks in Calendar
Finalize Proposal
23 Oct – 31 Oct
Project Module:
  Display Task Metrics
  End/Delete Project
  End/Delete Sub-Projects
  View Staff Availability from Dashboard
Staff Module:
  Sort/Filter Staff List
  View Staff Availability
Prepare Acceptance
23 Dec – 1 Jan
Hardware Resource Module:
  Create/View/ Edit Hardware Resource
  Assign Hardware to Project
Project Module:
  Notification Log
4 Jan – 17 Jan
User Account Module:
  Upload Profile Picture
  Deactivate Account
Staff Module:
  Upload Profile Picture
  Deactivate Staff
Quotation Module:
  Deactivate Quotation
Invoice Module:
  Deactivate Invoice
Contract Module:
  Deactivate Contract
Sign-Off Module:
  Deactivate Sign-off
Bug Logbook Module:
  Deactivate Bug Logbook
NDA Module:
  Deactivate NDA
20 Jan – 6 Feb
Business Intelligence:
  Generate Staff & Project Charts
  Sort Staff Chart
  Sort Project Chart
User Account Module:
  User Access Control
  Time-based Security
Optimization:
  Enhance UI
  Update APIs
10 Feb – 21 Feb (Target Go-Live)
Optimization:
  Dynamic Page Replacing Content
  Update APIs
Project Module:
  News Feed
Prepare for Midterm
28 Feb – 14 Mar
Improve from User Feedback
Project Module:
  Export to CSV
Quotation Module:
  Export to CSV
Invoice Module:
  Export to CSV
17 Mar – 28 Mar
Tidy Up Codes
Optimization:
  Enhance UI
Explore Optional Features
Prepare for Poster
31 Mar – 10 Apr
Project Closure
Prepare for Final Presentation
Prepare for Poster Day
5 Dec – 19 Dec
Master Setup Module:
  Create/View/Edit Document Templates
  Create/View/Edit Preset Quotation Modules
Quotation Module:
  Create/View/Edit Quotation with Preset Modules
Quotation, Invoice, Contract, Sign-Off, NDA Modules:
  Generate in PDF
  Email to Client
Bug Logbook Module:
  Generate in PDF
Debug from UAT
24 Sept – 8 Oct
Project Module:
  Create/View/Edit using Trello APIs
  View Project Details
Staff Module:
  Create/Edit Staff
  View Staff List
  View Staff Portfolio
6 Nov – 16 Nov
Project Module:
  Integrate Trello-Created Projects and Tasks to Own System
Quotation Module:
  Create/View/Edit Quotation w/o Preset Modules
  Create Payment Plan
Invoice, Contract, Sign-Off, Bug Logbook, NDA Modules:
  Create/View/Edit
2
3
4
5
6
7
8
9
10
11
12
13
14
15
Acceptance
3-5 Nov
Midterm
24 – 27 Feb
Poster
30 Mar
Final
Presentation
13 – 21 Apr
Poster Day
22 Apr
1st UAT
2nd UAT
3rd UAT

## Slide 6: Project timeline ver 3.0
Amended start/end date of iterations 5 & 6 due to delay in iteration 4

## Slide 7
1
Proposal
20 Oct
30 Jul – 7 Aug
Brainstorming Session
Project Initiation
Client Interaction
Proposal Planning
25 Aug – 9 Sept
UI Mockup
Use Case
Risk Mitigation Plans
Metrics Structure
Research & Learn
Set Up Environment
11 Sept – 21 Sept
Set Up Database
User Account Module:
  Login/Logout
  Create/Edit Account
  Password Reset
Learn to integrate with Trello
17 Oct – 25 Oct
Project Module:
  Create/Edit Sub-Projects
  View Sub-Projects in Project Schedule
  Create Dashboard
  Create Simulation on Dashboard
  Create Project from Simulation
Staff Module:
  View Projects in Staff Portfolio
  View Tasks in Calendar
Finalize Proposal
27 Oct – 1 Nov
Project Module:
  Display Task Metrics
  View Staff Availability from Dashboard
Staff Module:
  Sort/Filter Staff List
  View Staff Availability
Prepare Acceptance
23 Dec – 1 Jan
Hardware Resource Module:
  Create/View/ Edit Hardware Resource
  Assign Hardware to Project
Project Module:
  Notification Log
4 Jan – 17 Jan
User Account Module:
  Upload Profile Picture
  Deactivate Account
Staff Module:
  Upload Profile Picture
  Deactivate Staff
Quotation Module:
  Deactivate Quotation
Invoice Module:
  Deactivate Invoice
Contract Module:
  Deactivate Contract
Sign-Off Module:
  Deactivate Sign-off
Bug Logbook Module:
  Deactivate Bug Logbook
NDA Module:
  Deactivate NDA
20 Jan – 6 Feb
Business Intelligence:
  Generate Staff & Project Charts
  Sort Staff Chart
  Sort Project Chart
User Account Module:
  User Access Control
  Time-based Security
Optimization:
  Enhance UI
  Update APIs
10 Feb – 21 Feb (Target Go-Live)
Optimization:
  Dynamic Page Replacing Content
  Update APIs
Project Module:
  News Feed
Prepare for Midterm
28 Feb – 14 Mar
Improve from User Feedback
Project Module:
  Export to CSV
Quotation Module:
  Export to CSV
Invoice Module:
  Export to CSV
17 Mar – 28 Mar
Tidy Up Codes
Optimization:
  Enhance UI
Explore Optional Features
Prepare for Poster
31 Mar – 10 Apr
Project Closure
Prepare for Final Presentation
Prepare for Poster Day
5 Dec – 19 Dec
Master Setup Module:
  Create/View/Edit Document Templates
  Create/View/Edit Preset Quotation Modules
Quotation Module:
  Create/View/Edit Quotation with Preset Modules
Quotation, Invoice, Contract, Sign-Off, NDA Modules:
  Generate in PDF
  Email to Client
Bug Logbook Module:
  Generate in PDF
Debug from UAT
24 Sept – 8 Oct
Project Module:
  Create/View/Edit using Trello APIs
  View Project Details
Staff Module:
  Create/Edit Staff
  View Staff List
  View Staff Portfolio
6 Nov – 16 Nov
Project Module:
  End/Delete Project
  End/Delete Sub-Projects
  Integrate Trello-Created Projects and Tasks to Own System
Quotation Module:
  Create/View/Edit Quotation w/o Preset Modules
  Create Payment Plan
Invoice, Contract, Sign-Off, Bug Logbook, NDA Modules:
  Create/View/Edit
2
3
4
5
6
7
8
9
10
11
12
13
14
15
Acceptance
3-5 Nov
Midterm
24 – 27 Feb
Poster
30 Mar
Final
Presentation
13 – 21 Apr
Poster Day
22 Apr
1st UAT
2nd UAT
3rd UAT

## Slide 8: Project timeline ver 4.0
Amended tasks for some iterations due to change in UI requirements

## Slide 9
1
Proposal
20 Oct
30 Jul – 7 Aug
Brainstorming Session
Project Initiation
Client Interaction
Proposal Planning
25 Aug – 9 Sept
UI Mockup
Use Case
Risk Mitigation Plans
Metrics Structure
Research & Learn
Set Up Environment
11 Sept – 21 Sept
Set Up Database
User Account Module:
  Login/Logout
  Create/Edit Account
  Password Reset
Learn to integrate with Trello
17 Oct – 25 Oct
Project Module:
  Create/Edit Project Tasks
  View Project Tasks in Project Schedule
  Create Dashboard
  Create Simulation
  Create Project from Simulation
Staff Module:
  View Projects in Staff Portfolio
  View Tasks in Calendar
Finalize Proposal
27 Oct – 1 Nov
Project Module:
  Create Summary Page
Staff Module:
  Sort/Filter Staff List
  Create Summary Page
Prepare Acceptance
23 Dec – 1 Jan
Hardware Resource Module:
  Create/View/ Edit Hardware Resource
  Assign Hardware to Project
Project Module:
  Notification Log
4 Jan – 17 Jan
User Account Module:
Upload Profile Picture
Deactivate Account
Staff Module:
Upload Profile Picture
Deactivate Staff
Quotation, Invoice, Contract, Sign-Off, Bug Logbook, NDA Modules:
Deactivate
Debug from UAT
20 Jan – 6 Feb
Business Intelligence:
  Generate Staff & Project Charts
  Sort Staff Chart
  Sort Project Chart
User Account Module:
  User Access Control
  Time-based Security
Optimization:
  Enhance UI
  Update APIs
Debug from UAT
10 Feb – 21 Feb (Target Go-Live)
Optimization:
  Dynamic Page Replacing Content
  Update APIs
Project Module:
  News Feed
Debug from UAT
Prepare for Midterm
28 Feb – 14 Mar
Improve from User Feedback
Project Module:
  Export to CSV
Quotation Module:
  Export to CSV
Invoice Module:
  Export to CSV
17 Mar – 28 Mar
Tidy Up Codes
Optimization:
  Enhance UI
Explore Optional Features
Prepare for Poster
31 Mar – 10 Apr
Project Closure
Prepare for Final Presentation
Prepare for Poster Day
5 Dec – 19 Dec
Master Setup Module:
  Create/View/Edit Document Templates
  Create/View/Edit Preset Quotation Modules
Quotation Module:
  Create/View/Edit Quotation with Preset Modules
Quotation, Invoice, Contract, Sign-Off, NDA Modules:
  Generate in PDF
  Email to Client
Bug Logbook Module:
  Generate in PDF
Debug from UAT
24 Sept – 8 Oct
Project Module:
  Create/View/Edit using Trello APIs
  View Project Details
Staff Module:
  Create/Edit Staff
  View Staff List
  View Staff Portfolio
6 Nov – 16 Nov
Project Module:
  End/Delete Project
  End/Delete Project Tasks
  Integrate Trello-Created Projects and Tasks to Own System
Quotation Module:
  Create/View/Edit Quotation w/o Preset Modules
  Create Payment Plan
Invoice, Contract, Sign-Off, Bug Logbook, NDA Modules:
  Create/View/Edit
2
3
4
5
6
7
8
9
10
11
12
13
14
15
Acceptance
3 Nov
Midterm
24 – 27 Feb
Poster
30 Mar
Final
Presentation
13 – 21 Apr
Poster Day
22 Apr
1st UAT
2-3 Jan
2nd UAT
17-19 Jan
3rd UAT
7-9 Feb