## Project Timeline
Iteration | Start Date | End Date | Est. Num of Days | Buffer Start Date | Buffer End Date | Number of Buffer | Start Date | End Date | Act. Num of Days | Buffer Used | Metrics | Status
1 | 2014-07-30 | 2014-08-07 | 9 | 2014-08-08 | 2014-08-09 | 2 | 2014-07-30 | 2014-08-07 | 9 | 0 | 100 | On-time
2 | 2014-08-25 | 2014-09-09 | 16 | 2014-09-10 | 2014-09-10 | 1 | 2014-08-25 | 2014-09-09 | 16 | 0 | 100 | On-time
3 | 2014-09-11 | 2014-09-21 | 11 | 2014-09-22 | 2014-09-23 | 2 | 2014-09-11 | 2014-09-23 | 13 | 2 | 84.6154 | Late
4 | 2014-09-24 | 2014-10-08 | 15 | 2014-10-09 | 2014-10-11 | 3 | 2014-09-24 | 2014-10-16 | 23 | 3 | 65.2174 | Late
5 | 2014-10-17 | 2014-10-25 | 9 | 2014-10-26 | 2014-10-26 | 1 | 2014-10-17 | 2014-10-26 | 10 | 1 | 90 | Late
6 | 2014-10-27 | 2014-11-01 | 6 | 2014-11-02 | 2014-11-02 | 1 | 2014-10-27
7 | 2014-11-06 | 2014-11-16 | 11 | 2014-11-17 | 2014-11-18 | 2
8 | 2014-12-05 | 2014-12-19 | 15 | 2014-12-20 | 2014-12-22 | 3
9 | 2014-12-23 | 2015-01-01 | 10 | 2015-01-02 | 2015-01-03 | 2
10 | 2015-01-04 | 2015-01-17 | 14 | 2015-01-18 | 2015-01-19 | 2
11 | 2015-01-20 | 2015-02-06 | 18 | 2015-02-07 | 2015-02-09 | 3
12 | 2015-02-10 | 2015-02-21 | 12 | 2015-02-22 | 2015-02-23 | 2
13 | 2015-02-28 | 2015-03-14 | 15 | 2015-03-15 | 2015-03-16 | 2
14 | 2015-03-17 | 2015-03-28 | 12 | 2015-03-29 | 2015-03-29 | 1
15 | 2015-03-31 | 2015-04-10 | 11 | 2015-04-11 | 2015-04-12 | 2
End Date > Start Date | Buffer End > Buffer Start
TRUE | TRUE
TRUE | TRUE
TRUE | TRUE
TRUE | TRUE
TRUE | TRUE
TRUE | TRUE
TRUE | TRUE
TRUE | TRUE
TRUE | TRUE
TRUE | TRUE
TRUE | TRUE
TRUE | TRUE
TRUE | TRUE
TRUE | TRUE
TRUE | TRUE
Formulas:
Buffer Start Date = [End Date]+1
Buffer End Date = [Buffer Start Date]+[Number of Buffer]-1
Start Date = [Buffer End Date, row above]+1
Start Date = [End Date, row above]+1
Note on B4: Elaine: Why a long break after iter 1? Members went on holidays. Decided to hold the project progress until everyone could regroup again
Note on I4: Elaine: Why a long break after iter 1? Members went on holidays. Decided to hold the project progress until everyone could regroup again
Note on B6: Elaine: Iteration is long in view of mid-term papers
Note on B7: Elaine: Changed from 12 Oct
Note on C7: Elaine: Changed from 21 Oct
Note on H7: Elaine: Milestone: 2 page proposal submission
Note on H8: Elaine: Note the empty dates 3 - 5 Nov (Acceptance milestone)
Note on B9: Elaine: Start iteration after milestone Acceptance
Note on H9: Elaine: Study Break 19 Nov - 4 Dec 2014
Note on B10: Elaine: Regroup after study break
Note on B15: Elaine: Start iteration after milestone Mid-term
Note on B17: Elaine: Start iteration after milestone Poster Day