## Bug Logbook
Bug Metrics (Iteration 3)
ID | Bug Description | Impact | Score | Date Found | Found By | Source | Server | Resolved? | Resolved By | Date Resolved | Solution
1 | Reset password page is not being redirected to login page after user has inputted new password and clicked on 'Continue' button. | Low | 1 | 2014-09-22 | Li Dan, Yining | login.scala | Localhost | Yes | Annan | 2014-09-23 | Changed in "resetPassword.js" to prevent the redirecting of page.
2 | No error message is displayed when user keys the wrong email address to send reset password URL to. Login page is redirected, which shouldn't be the case. | Low | 1 | 2014-09-22 | Li Dan, Yining | login.scala | Localhost | Yes | Annan | 2014-09-23 | Inserted error message in "login.js" for when user inputs wrong email address.
3 | New password was not successfully resetted after user clicks on 'Continue' in reset password page | High | 5 | 2014-09-22 | Li Dan, Yining | login.scala | Localhost | Yes | Annan | 2014-09-23 | Changed in "resetPassword.js" to store the new password in database.
4 | No error message is displayed when user keys in different confirmation password from the new password in reset password paage after user clicks on 'Continue' | Low | 1 | 2014-09-22 | Li Dan, Yining | login.scala | Localhost | Yes | Annan | 2014-09-23 | Added new input validation in "resetPassword.js" to display error message when user inputs wrong confirmation password from the new password.
5 | There is no auto-generation of password when creating a new staff | High | 5 | 2014-09-22 | Li Dan, Yining | adminStaff.scala | Localhost | Yes | Annan, Yining | 2014-09-23 | Added new function into "AccountManager.java" to auto-generate password.
6 | A new user is created even though the email address is incorrect | High | 5 | 2014-09-22 | Li Dan, Yining | adminAccount.scala | Localhost | Yes | Annan | 2014-09-23 | Added front-end input validation to check email address in "adminAccount.js".
7 | Unable to edit an existing user | Critical | 10 | 2014-09-22 | Li Dan, Yining | adminAccount.scala | Localhost | Yes | Annan | 2014-09-23 | Added updateAccount function into "editAccount.js" to allow user to edit user information.
8 | No clickable link is provided in the email when user forgets password. User has to manually copy and paste the given link in web browser | Low | 1 | 2014-09-22 | Li Dan, Yining | adminAccount.scala | Localhost | Yes | Annan | 2014-09-23 | Change method in "Application.java" to provide clickable link in email sending function

## Bug Metrics Summary
Iteration | Low | High | Critical | Total Score | Action Taken
3 | 4 | 3 | 1 | 29 | Stop current development and resolve the bug immediately. Use up buffer days to debug.

## Action Plan
Points in Iteration | Action Plan
< 20 | Use planned debugging time in iteration
>= 20 | Stop current development and resolve the bug immediately. Reschedule project.

## Severity Value Description
Severity in Value | Bug Description
Low Impact (1 point) | Typo errors, basic UI alignment issues.
High Impact (5 points) | Some non-critical functionalities not working as expected. Overall application still runs.
Critical Impact (10 points) | Entire system is down or unusable. Team to stop and fix bugs before continuing