## Bug Logbook
Bug Metrics (Iteration 4)
ID | Bug Description | Impact | Score | Date Found | Found By | Source | Server | Resolved? | Resolved By | Date Resolved | Solution
1 | Reset password page is being redirected to login page after user has inputted mismatched new password and confirm password and clicked on 'Continue' button. | Low | 1 | 2014-10-13 | Elaine, Annan | resetPassword.scala | Localhost | Yes | LiDan | 2014-10-13 | Changed in resetPassword.js to prevent the redirecting of page.
2 | User is unable to log in with his old password after inputting the mismatched 'new' and 'confirm' passwords in the reset password page. E.g. current password = 123 new password = 456 confirm password = 789 Now, user cannot log in with 123. | High | 5 | 2014-10-13 | Elaine, Annan | login.scala | Localhost | Yes | LiDan | 2014-10-13 | Changed in resetPassword.js to prevent updating password when passwords are not matching.
3 | User is able to view web app pages by entering the page url even though he has logged out of the system. | Low | 1 | 2014-10-13 | Elaine, Annan | login.scala | Localhost | Yes | LiDan | 2014-10-13 | Changed in adminAcount.js, adminStaff.js, dashboard.js, project.js, staff.js to prevent users from entering the pages.
4 | Admin cannot edit an existing user account's email address, name and password successfully. No update was done to the account list on the changes made. | High | 5 | 2014-10-13 | Elaine, Annan | adminAccount.scala | Localhost | Yes | Yining | 2014-10-14 | Changed the disabled column from "name" to "username".
5 | Admin can change the username of a user account, which should not be the case since username cannot be changed once created. | Low | 1 | 2014-10-13 | Elaine, Annan | adminAccount.scala | Localhost | Yes | LiDan | 2014-10-13 | Changed in adminAcount.js to prevent users from modifying username.
6 | Invalid email address can be updated in user account page when user inputs an invalid email address when editing his account. | Low | 1 | 2014-10-13 | Elaine, Annan | editAccount.scala | Localhost | Yes | Yining | 2014-10-14 | Insereted error message in "admin.js" when invalid email address is inputed.
7 | Staff management page is redirected to account management page when user clicks on the 'Edit' button and then the 'Save' button in staff management page. | High | 5 | 2014-10-13 | Elaine, Annan | adminStaff.scala | Localhost | Yes | LiDan | 2014-10-13 | Changed in adminStaff.js to prevent the redirecting of page.
8 | Staff information is not updated in staff management page when user updates staff's information. | High | 5 | 2014-10-13 | Elaine, Annan | adminStaff.scala | Localhost | Yes | Yining | 2014-10-14 | StaffManager.java is modified and fix the bug by adding two more requested attributes to the updateStaffInfo method
9 | No error message is displayed when user inputs negative value for 'max no. of projects'. | Low | 1 | 2014-10-13 | Elaine, Annan | adminStaff.scala | Localhost | Yes | LiDan | 2014-10-13 | Changed in project.js to prevent the users from entering negative value for max project number.
10 | No error message is displayed when user inputs more or less than 3 letters for client abbreviation when creating a project. | Low | 1 | 2014-10-13 | Elaine, Annan | project.scala | Localhost | Yes | LiDan | 2014-10-13 | Changed in project.js to prevent users entering < or > 3 letters.
11 | List of project managers is not populated in the creating of a project card. | High | 5 | 2014-10-13 | Elaine, Annan | project.scala | Localhost | Yes | Yining | 2014-10-14 | Changed in ProjectController.java and add a method to populate the assigned Project Manager to both project table and project_staff table.
12 | List of staffs is not populated in the creating of a project card. | High | 5 | 2014-10-13 | Elaine, Annan | project.scala | Localhost | Yes | Yining | 2014-10-14 | Changed in ProjectController.java and add a method to populate the assigned staffs to the project_staff table.
13 | Error message on the end date 'The end date cannot be less than the start date' occurs even before user manually inputs an end date, which should not be the case. It should only appear when user selects a date that is earlier than the selected start date. | Low | 1 | 2014-10-13 | Elaine, Annan | project.scala | Localhost | Yes | LiDan | 2014-10-13 | Changed in project.js to prevent the error message showing before users enter end date.
14 | End date was not auto-populated when user selects a duration of either 3 or 6 months. | Low | 1 | 2014-10-13 | Elaine, Annan | project.scala | Localhost | Yes | LiDan | 2014-10-13 | Changed in project.js to autopopulate end date.
15 | Pop up page for the creation of a new project disappears when user clicks on 'Create' button, even when there are errors with his inputs. Page should have remained instead of disappeared. Error messages for the errors should have been displayed instead. | Critical | 10 | 2014-10-13 | Elaine, Annan | project.scala | Localhost | Yes | LiDan | 2014-10-13 | Changed in project.scala.html to prevent the pop up from disappearing when there are still errors.
16 | No error message is displayed when user inputs invalid start date when creating a new project. | Low | 1 | 2014-10-13 | Elaine, Annan | project.scala | Localhost | Yes | LiDan | 2014-10-13 | Changed in project.js to provide error message when users input invalid start date.
17 | No error message is displayed when user inputs invalid end date when creating a new project. | Low | 1 | 2014-10-13 | Elaine, Annan | project.scala | Localhost | Yes | LiDan | 2014-10-13 | Changed in project.js to provide error message when users input invalid start date.
18 | No error message is displayed when user inputs a start date that has past when creating a new project, e.g. 2013/01/01. | Low | 1 | 2014-10-13 | Elaine, Annan | project.scala | Localhost | Yes | LiDan | 2014-10-13 | Changed in project.js to provide error message when users input invalid start date.
19 | No error message is displayed when user inputs invalid end date that has past when creating a new project, , e.g. 2013/01/01. | Low | 1 | 2014-10-13 | Elaine, Annan | project.scala | Localhost | Yes | LiDan | 2014-10-13 | Changed in project.js to provide error message when users input start date that is passed.
20 | No 'edit' button for user to edit an existing project. | Critical | 10 | 2014-10-13 | Elaine, Annan | project.scala | Localhost | Yes | LiDan | 2014-10-13 | Changed in project.js to provide error message when users input end date that is passed.
21 | Duration for 3 and 6 months when creating a new project is not highlighted when user clicks on either one, whereas 'Others' option is highlighted in darker grey tone when selected. | Low | 1 | 2014-10-13 | Elaine, Annan | project.scala | Localhost | Yes | LiDan | 2014-10-13 | Changed in project.js to allow 3 and 6 months to be selected even though start date has not been entered.
22 | Information on 'last modified on', 'last modified by', 'project manager', 'staffs' is not displayed on project details page. | Low | 1 | 2014-10-13 | Elaine, Annan | project.scala | Localhost | Yes | Yining | 2014-10-14 | Changed in Porject.java, ProjectManager.java and ProjectController.java. Add methods to check the last modified account, modified date and the staffs assigned (including PM).

## Bug Metrics Summary
Iteration | Low | High | Critical | Total Score | Action Taken
3 | 4 | 3 | 1 | 29 | Stop current development and resolve the bug immediately. Use up buffer days to debug.
4 | 14 | 6 | 2 | 64 | Stop current development and resolve the bug immediately. Use up buffer days to debug.

## Action Plan
Points in Iteration | Action Plan
< 20 | Use planned debugging time in iteration
>= 20 | Stop current development and resolve the bug immediately. Reschedule project.

## Severity Value Description
Severity in Value | Bug Description
Low Impact (1 point) | Typo errors, basic UI alignment issues.
High Impact (5 points) | Some non-critical functionalities not working as expected. Overall application still runs.
Critical Impact (10 points) | Entire system is down or unusable. Team to stop and fix bugs before continuing